## Thread Map
Where Everything Sits - Four Parallel Threads
Orientation sheet. Nothing here is a deliverable; it exists so nobody loses the plot.
Thread | What it is | Where it lives | Status | Next action
1. Requirements baseline | The stakeholder's 16 bullets, normalised to 170 candidate transactions, split into streams A/B/C/D. The core engagement. | S4_2022_Fiori_Transaction_Baseline_v3.xlsx | Run 1 complete (manual). Run 2 pending ST03N. | Chase BASIS. Confirm Web Dynpro + OData task types are included, not just the transaction profile.
2. Purchase orders - first evaluation target | Agreed in the meeting as the starting point because PO transactions carried the highest relevance scores. The recommendation output you screenshotted is this thread. | THIS workbook - 'Recommended Apps' sheet | ACTIVE. 24 apps identified for the Purchaser role. | Pull implementation info for the Wave 1 apps and hand to security.
3. Cost analysis | F3567, F1780, F6991. Arrived by email Friday evening, separate from the meeting. Does NOT map to any of the 16 stakeholder requirements - closest is R-12 and it is not close. | This workbook - flagged in 'Recommended Apps' as Thread 3 | PARKED. Provenance unclear. | Ask where this came from before it enters the matrix. Either there is a requirements thread you have not been read into, or it is adjacent exploration.
4. Evaluation access | DEV/QAS launchpad access so you can search apps, confirm what is really activated, and run a light demo. | This workbook - 'Role Request' and 'App Detail' | ACTIVE. In conversation with security. | Send Role Request first. App Detail only for exceptions.
THREAD 2 IS THE ONE THAT MOVES THIS WEEK
- Purchase orders were chosen for good reason - the relevance scores back it up, the apps are all showing Installed, and it is a self-contained demo story.
- The Purchaser role returned 24 apps. That is a demo shortlist problem, not a coverage problem. Wave 1 on the 'Recommended Apps' sheet narrows it to five.
- Source lists and purchasing info records came back under Purchaser too. You are right that they matter - they are R-03 on the requirements baseline, and they are data objects in the migration scope. Wave 2.

## Recommended Apps
Fiori App Recommendation Output - Purchaser Role
Transcribed from your recommendation analysis run, filtered to RoleName = Purchaser. Purple columns are output from that run. Blue columns are yours to fill from the library. Amber is security. F1663A is flagged Deprecated/Obsolete - exclude it from the catalog and the demo.
IDENTIFICATION | [6 empty] | RECOMMENDATION OUTPUT (from your run) |  |  |  | LIBRARY IMPLEMENTATION INFO (pull per app) | [5 empty] | SECURITY ACTION
# | App ID | App name | App type | Role name(s) | Req ref | Wave | System readiness | Relevance | Source transactions | Lifecycle | Business catalog | Technical catalog | Primary OData service | Additional OData | BSP / UI5 app | Available as of | IWSG active | IWSV active | PFCG role assigned | Security notes
1 | F0842A | Manage Purchase Orders (Version 2) | Transactional | Purchaser ¦ Purchaser - Central Procurement | R-09 | 1 | Installed | *** | ME23N, ME22N, ... | Current Version Candidate | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | The 'purchase orders' app you remembered. Core of the Wave 1 demo.
2 | F2358 | Monitor Purchase Order Items | Analytical | Inventory Manager ¦ Purchaser ¦ Warehouse Clerk | R-09 | 1 | Installed | *** | ME2W, ME2L, ME2N, ... | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | The 'purchase order line items' app. Spans three roles - strongest demo piece because it crosses personas, and ME2W is the STO-specific view from R-09.
3 | F3791 | Purchase Order Changes | Analytical | Strategic Buyer ¦ Purchaser | R-09 | 1 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | DIRECT HIT on the 'including change history' half of R-09. Demo this one deliberately.
4 | F0343 | Overdue Purchase Order Items | Analytical | Strategic Buyer ¦ Purchaser | R-09 | 1 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Exception-based monitoring. Good demo contrast to the list apps.
5 | F0547B | My Purchasing Document Items | Transactional | Purchaser | R-08, R-09 | 1 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Personalised worklist. Shows the role-based UX story well.
6 | F1859 | Manage Source Lists | Transactional | Purchaser | R-03 | 2 | Installed | *** | ME0M, ME01, ME03 | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | R-03 data object. Migration validation surface - inspect migrated source lists, not a load tool.
7 | F1982 | Manage Purchasing Info Records | Transactional | Purchaser | R-03 | 2 | Installed | *** | ME1M, ME12, ME1L, ... | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | R-03 data object. Same migration validation role.
8 | F0840A | Manage Sources of Supply (Version 2) | Transactional | Purchaser | R-03 | 2 | Installed | *** | ME31K, ME01, ME11 | Current Version Candidate | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Umbrella over source list, info record and contract. May consolidate several Wave 2 apps - check overlap before requesting all four.
9 | F1600A | Manage Purchase Contracts (Version 2) | Transactional | Purchaser | R-03 | 2 | Installed | *** | MEK2, ME31K, ... | Current Version Candidate | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | R-03 contracts. MEK2 in the source list means pricing conditions are in play - check whether scales are exposed.
10 | F2988 | Monitor Purchasing Info Records Price History | Analytical | Purchaser | R-03 | 2 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | DIRECT HIT on the historical half of R-03. This is the ME1P successor I previously said had no clean Fiori answer - correction, it does.
11 | F2229 | Manage Purchase Requisition Professional | Transactional | Purchaser | R-08 | 2 | Installed | *** | ME51N, ME52N, ... | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Core PR maintenance.
12 | F1048 | Process Purchase Requisitions | Transactional | Purchaser | R-08 | 2 | Installed | *** | ME57 | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Assignment and processing.
13 | F2424 | Monitor Purchase Requisition Items | Analytical | Purchaser | R-08 | 2 | Installed | *** | MELB, ME58, ME5A | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | The 'all requisitions' list view.
14 | F2015 | Purchase Requisition Item Changes | Analytical | Strategic Buyer ¦ Purchaser | R-08 | 2 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | DIRECT HIT on the change-history half of R-08.
15 | F2594 | Mass Changes to Purchase Requisitions | Transactional | Purchaser | R-08 | 2 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Mass change - normally a Fiori gap, so worth noting it exists here.
16 | F0682 | Invoice Price Variance | Analytical | Strategic Buyer ¦ Purchaser | R-12 | 3 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Relates to the 'pricing errors' half of R-12.
17 | F3294 | Material Price Variance | Analytical | Strategic Buyer ¦ Purchaser | R-03, R-12 | 3 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC
18 | F1377 | Spend Variance | Analytical | Strategic Buyer ¦ Purchaser | (none) | 3 | Installed | ** | (transaction group) | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | No requirement maps to this. Nice-to-have.
19 | F2359 | Monitor Supplier Confirmations | Analytical | Purchaser | R-10 | 2 | Installed | *** | ME2A | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Confirms the R-10 reading - supplier acknowledgements, not production confirmations. Q3 effectively answered.
20 | F0859 | Manage Supplier Invoices | Transactional | Accounts Payable Accountant - Procurement ¦ General Ledger | R-12 | 3 | Installed | *** | MIR7, MR8M, MIRO | No warning | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | NOT a Purchaser-role app - AP Accountant. Needs a different role assignment than the rest of this sheet.
21 | F1662A | Operational Supplier Evaluation (Version 2) | Analytical | Strategic Buyer ¦ Purchaser | (none) | 3 | Installed | ** | (transaction group) | Current Version Candidate | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | No requirement maps to supplier evaluation.
22 | F1661A | Supplier Evaluation by Quantity (Version 2) | Analytical | Strategic Buyer ¦ Purchaser | (none) | 3 | Installed | ** | (transaction group) | Current Version Candidate | TBC | TBC | TBC | TBC | TBC | TBC
23 | F1664A | Supplier Evaluation by Time (Version 2) | Analytical | Strategic Buyer ¦ Purchaser | (none) | 3 | Installed | ** | (transaction group) | Current Version Candidate | TBC | TBC | TBC | TBC | TBC | TBC
24 | F1663A | Supplier Evaluation by Price (Version 2) | Analytical | Strategic Buyer ¦ Purchaser | (none) | EXCLUDE | Installed | ** | (transaction group) | Deprecated/Obsolete | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | EXCLUDE. Deprecated/Obsolete per your own run. Do not put in a catalog or the demo. Check the library for a successor if supplier price evaluation is actually wanted.
25 | F3567 | Actual Maintenance Cost Analysis | Transactional | Maintenance Planner | (Thread 3) | 3 | TBC | n/a | n/a | TBC | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Thread 3 - Friday email. Verified: leading role SAP_BR_MAINTENANCE_PLANNER, OData EAM_ORDER_ACTUALCOST_MONITOR, BSP EAM_ACOST_MONS1. Note the name was truncated to 'Cost Analysis' in the agent output.
26 | F1780 | Production Cost Analysis | Transactional | Controller - Production Costs | (Thread 3) | 3 | TBC | n/a | n/a | TBC | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Thread 3. Replaces S_ALR_87013127.
27 | F6991 | Project Cost Overview | Analytical | TBC | (Thread 3) | 3 | TBC | n/a | n/a | TBC | TBC | TBC | TBC | TBC | TBC | TBC |  |  |  | Thread 3. Available from S/4HANA 2022 FPS1.
WAVE DEFINITIONS
Wave 1 (5 apps) |  | Purchase order demo set. Self-contained story: maintain, monitor, exception, change history, personal worklist. This is what you request access for first.
Wave 2 (10 apps) |  | Sourcing data objects and requisitions. Covers R-03 and R-08. Relevant to the migration effort as validation surfaces.
Wave 3 |  | Analytics and variance, plus the Thread 3 cost apps. Not needed for the first demo.
EXCLUDE |  | F1663A only. Deprecated/Obsolete.

## Role Request
Delivered Business Role Assignment (Primary Ask)
Send this first. Purchaser now leads - it is the role behind the Wave 1 demo. Verify exact technical names in the library before submitting; the flagged rows are ones I am not confident enough about.
# | SAP business role template | Persona / description | Covers | System | Client | User ID(s) | Security status
1 | SAP_BR_PURCHASER | Operational purchaser - the role behind all 24 recommended apps. PRIMARY ASK for the Wave 1 demo. | R-03, R-08, R-09, R-10 | DEV
2 | SAP_BR_PURCHASER_CENTRAL | Central procurement purchaser - second role on F0842A. Verify exact name. | R-09 | DEV
3 | SAP_BR_BUYER | Strategic buyer - second role on the analytics and variance apps. Verify exact name. | R-09, R-12 | DEV
4 | SAP_BR_INVENTORY_MANAGER | Inventory manager - also carries F2358, and covers stock inquiry and physical inventory. | R-05, R-06, R-15 | DEV
5 | SAP_BR_WAREHOUSE_CLERK | Warehouse clerk - also carries F2358. Goods movements, picking. | R-13, R-15 | DEV
6 | SAP_BR_AP_ACCOUNTANT | AP accountant - required for F0859, which is NOT a Purchaser app. | R-12 | DEV
7 | SAP_BR_MAINTENANCE_PLANNER | Maintenance planner - F3567. Thread 3, and the MRO hypothesis. | Thread 3, R-06 | DEV
8 | SAP_BR_MATERIAL_PLANNER | Material planner - MRP and coverage. | R-06, R-07 | DEV
9 | SAP_BR_PRODUCTION_PLANNER | Production planner - planned independent requirements. | R-07 | DEV
10 | SAP_BR_SHIPPING_SPECIALIST | Shipping specialist - inbound/outbound deliveries. | R-11, R-13 | DEV
11 | (verify) Product master specialist | Material master. Confirm exact SAP_BR_* name in library. | R-01 | DEV
12 | (verify) Business partner master | Vendor / BP master data. Confirm exact SAP_BR_* name in library. | R-04 | DEV
If SoD is raised:
- Ask for display-variant roles where SAP delivers them, or Z copies with create/change catalogs stripped.
- Offer to scope to specific plants or purchasing organisations rather than open assignment.
- State the access is time-boxed to the evaluation window with a fixed revocation date.

## OData Services
Consolidated OData Service Activation List
Deduplicated from Recommended Apps. This is what security actually activates - apps share services, so working by service is far less effort than app by app. Populate as you pull implementation info.
# | OData service name | Version | Used by App ID(s) | IWSG active | IWSV active | Notes
1 | EAM_ORDER_ACTUALCOST_MONITOR |  | F3567 |  |  | Verified from library. Thread 3.

## Validation Log
Post-Provisioning Validation
Three separate failure modes with three different owners. A tile that appears but errors on open is an ACTIVATION gap, not an app missing from 2022 - logging it as the latter corrupts the coverage matrix.
# | App ID | App name | Tile visible? | App opens? | Data returns? | Failure type | Notes / next action
1 | F0842A | Manage Purchase Orders (Version 2)
2 | F2358 | Monitor Purchase Order Items
3 | F3791 | Purchase Order Changes
4 | F0343 | Overdue Purchase Order Items
5 | F0547B | My Purchasing Document Items
6 | F1859 | Manage Source Lists
7 | F1982 | Manage Purchasing Info Records
8 | F0840A | Manage Sources of Supply (Version 2)
9 | F1600A | Manage Purchase Contracts (Version 2)
10 | F2988 | Monitor Purchasing Info Records Price History
11 | F2229 | Manage Purchase Requisition Professional
12 | F1048 | Process Purchase Requisitions
13 | F2424 | Monitor Purchase Requisition Items
14 | F2015 | Purchase Requisition Item Changes
15 | F2594 | Mass Changes to Purchase Requisitions
16 | F0682 | Invoice Price Variance
17 | F3294 | Material Price Variance
18 | F1377 | Spend Variance
19 | F2359 | Monitor Supplier Confirmations
20 | F0859 | Manage Supplier Invoices
21 | F1662A | Operational Supplier Evaluation (Version 2)
22 | F1661A | Supplier Evaluation by Quantity (Version 2)
23 | F1664A | Supplier Evaluation by Time (Version 2)
24 | F3567 | Actual Maintenance Cost Analysis
25 | F1780 | Production Cost Analysis
26 | F6991 | Project Cost Overview
READING THE THREE STATES
Tile not visible |  | Catalog not in an assigned role. Security - back to Role Request.
Tile visible, errors on open |  | OData service not activated, or SICF node inactive. Basis / Fiori admin, not security.
Opens, no data |  | Empty client, or org-level authorisation restricting selection. Establish which before assuming either.
Opens with data |  | Working. Now assess functional coverage against the requirement - the actual point.

## Field Guide
Where Each Value Lives in the Fiori Apps Reference Library
Deep link pattern: the external viewer takes an App ID directly - .../externalViewer/#/detail/Apps('F0842A')/... The classic library is being transitioned and is slated for discontinuation in December 2026, so confirm which viewer the team standardises on before building process around deep links.
Column | Where to find it | Why it matters
App ID | App detail header. | The only reliable key. Names get truncated by chat tools; IDs do not.
App name | App detail header. | Pull fresh. A dropped qualifier changes what an app is for.
App type / UI technology | App detail header. | Web Dynpro and GUI-for-HTML entries authorise differently from Fiori elements apps.
Business catalog | Implementation Information. | The catalog that must sit in the PFCG role for the tile to appear.
Technical catalog | Implementation Information. | Needed only when building a Z business catalog.
OData services | Implementation Information - services. | The real authorisation vector. Frontend (IWSG) and backend (IWSV) activate separately.
BSP / SAPUI5 app | Implementation Information. | Identifies the UI5 app and SICF node for activation troubleshooting.
Available as of | Release information. | Confirms the app exists in 2022. Listed as of 2023 means not a candidate.
Lifecycle status | App detail. | Deprecated/Obsolete is a hard stop. Confirm what your library means by 'Current Version Candidate' before treating it as a warning - it reads as the version to standardise on, not a problem.
Product version filter | Set BEFORE searching. | SAP S/4HANA 2022, private cloud and on-premise. Public Cloud results will not exist in your system.